## Slide 1
Alpha Manufacturing Group (AMG) - ERP Transformation
Executive review
A phased cloud ERP programme that protects operations, improves margin visibility, and preserves historical reporting.
~200 employees
Mid-sized industrial equipment manufacturer
5 locations
Operations in the US and Canada
~$100m revenue
Annual revenue base
Why the change now?
The current ERP landscape is fragmented, BOM sync is fragile, labour tracking is unreliable, and margin erosion is occurring on most custom orders. The board’s goal is not only to replace software - it is to stabilise operations and create a trusted management view of profitability.
12-month target
go-live
Pilot first
Minimal customisation
Archive history
Parallel close
Notes: Open by framing the assignment as a business transformation, not a software install. State that AMG is losing margin and operational control because its systems are fragmented and the BOM handoff is fragile. Explain that the recommendation is to go live in phases rather than attempt a big-bang cutover. Close by telling the audience that the deck balances speed with risk control, because uninterrupted operations matter more than feature completeness on Day 1.

## Slide 2
Executive summary and decision asks
What AMG should approve
1. Programme approach
Use a phased, pilot-first cloud ERP implementation with fit-to-standard design and strong change control.
2. Scope discipline
Put core finance, manufacturing, procurement, inventory, BOM accuracy, and order processing into Day 1. Defer CRM, HRIS and advanced analytics.
3. Data continuity
Migrate operational data, keep historical data in a reporting archive, and protect month-end close with a parallel run.
Executive decision requested
Approve the transformation principles, appoint business process owners and a steering committee, freeze Day-1 scope after design sign-off, and authorise a controlled pilot at one site before wider rollout.
Notes: This slide is the one-sentence answer for executives. Make it clear that the programme is designed to reduce risk, not chase every possible feature. The three decision asks are: approve the approach, approve strict scope control, and approve the data/archive strategy. If challenged, emphasise that AMG is not buying a new ERP for its own sake; it is buying operational reliability and margin transparency.

## Slide 3
Current-state business impact
Where the pain shows up today
Margin erosion
Most custom orders have poor cost visibility and hidden overruns.
BOM instability
Engineering updates do not always reach manufacturing in time.
Manual workarounds
Excel is used to patch gaps between disconnected systems.
Operational consequences
• Manufacturing delays when BOM sync fails
• Unreliable labour tracking and contribution margin reporting
• Duplicate data entry across systems
• Higher risk of rework, expedites, and missed delivery dates
• Executives cannot confidently see which orders are profitable
Notes: Use this slide to explain the business case in plain English. The company is not suffering from a lack of effort; it is suffering from disconnected systems and unreliable data flow. The key message is that margin erosion is a symptom of the current operating model. That is why the solution must fix process, data and governance together, rather than treating the ERP replacement as a technology-only project.

## Slide 4
Transformation principles
How AMG reduces implementation risk
Fit-to-standard
Start from the ERP’s standard processes, then identify only the necessary gaps.
Pilot first
Prove the model at one site before rolling out to the rest of the organisation.
Configure before customising
Use settings and extensions before changing core code.
Govern by value
Approve only changes that clearly improve control, compliance, or Day-1 readiness.
Operating rule
Every request is judged against four questions: does it help AMG run the plant, does it reduce risk, can it be delivered on time, and can it be supported after go-live?
Notes: This slide explains the logic behind the scope choices. Fit-to-standard means AMG adapts to proven ERP practices wherever possible. Pilot-first means the team learns on a smaller blast radius before scaling. Configure-before-customise avoids creating a second legacy system inside the new cloud ERP. Value-based governance keeps the board’s timeline and risk appetite in control.

## Slide 5
Current-state architecture
Fragmented systems and fragile data flow
Engineering DB
BOM and ECNs
Legacy ERP
Finance, MRP, procurement
CRM
Unintegrated
HRIS / Payroll
Siloed
Excel
Heavy reliance
Main failure points
Nightly fragile sync - BOM changes can arrive too late for production. Manual spreadsheets hide the true status of orders. Separate systems prevent a single trusted view of cost, labour and margin.
Notes: Walk the audience through the current architecture from left to right. The point is not that the company has too much technology, but that the technology is not joined up. BOM and ECN movement between engineering and ERP is especially risky because a one-day delay can disrupt manufacturing. Excel is acting as the integration layer, which usually means the business is carrying hidden process risk.

## Slide 6
Target architecture
A simpler cloud ERP hub with controlled integrations
Cloud ERP core
Finance | Manufacturing | Procurement | Inventory | Order processing
Engineering system
BOM / ECN master
CRM
Sales pipeline
Reporting archive
History + KPIs
HRIS
People data
Data governance
Owners | rules | approvals | quality checks
Design intent
The new ERP becomes the system of record for operations and finance, while other applications connect through governed interfaces. Historical reporting moves to an archive so the ERP stays fast and manageable.
Notes: Explain that the future state is intentionally simpler than the current one. The cloud ERP becomes the operational core, not a place where every possible function lives. Engineering, CRM, HR and reporting still matter, but they should connect cleanly rather than own separate islands of data. The benefit is better control, better visibility and fewer brittle point-to-point workarounds.

## Slide 7
Day-1 must-haves
What must work on the first go-live
Finance
• General ledger
• Accounts payable and receivable
• Fixed assets
• Month-end close
• Core controls and approvals
Operations
• Inventory
• Purchasing
• Production planning
• BOM and ECN handoff
• Basic labour capture
Commercial flow
• Order entry integration
• Customer and supplier master data
• Shipment and invoicing flow
• Essential customer service visibility
Control tower
• Core reports
• Exception alerts
• Go-live readiness checks
• Hypercare support
Notes: The message here is that Day 1 should cover only what is needed to run the business. Finance, manufacturing, purchasing and the BOM handoff are non-negotiable because they are the backbone of operations. The control tower block shows that reporting and support are part of go-live readiness, not an afterthought. Stress that the cutover set should be small enough to test deeply.

## Slide 8
Deliberately deferred scope
What should wait until after stabilisation
Defer from initial go-live
• Full CRM redesign
• Full HRIS / payroll replacement
• Advanced analytics and AI add-ons
• Broad workflow automation
• Non-essential user interface changes
Why defer?
These items add delivery risk but do not stop AMG from building, shipping and invoicing on Day 1.
Customization discipline
1. Start with standard functionality
2. Accept configuration before code changes
3. Require a business case for every exception
4. Reject “legacy in new clothes” requests
5. Push late changes into a later release
Notes: A strong candidate answer is that deferral is not denial. These items may still be valuable, but they are not required for a safe first go-live. The deck should make clear that the team is protecting the timeline and avoiding unnecessary code changes. Mention that customisation has a long-tail cost because it makes future upgrades and support more difficult.

## Slide 9
Data and reporting strategy
Keep history accessible without overloading the ERP
Operational data
Live master data + open items + current balances
New ERP
System of record for Day-1 operations
Archive / warehouse
Historical detail, trend analysis, audit support, KPI history
Month-end close continuity
Run a parallel close before cutover, compare totals, and keep the legacy ERP read-only until finance and audit are satisfied that reports and controls are stable.
Practical rule
Move what operations need now; archive what leadership still needs to see later.
Notes: This slide answers the “what happens to our history?” question. The safest pattern is to migrate live operational data into the ERP, while keeping older history in an archive or warehouse. That gives managers uninterrupted access to KPIs without forcing the new ERP to carry years of obsolete transactions. Month-end close must be proven through a parallel run before the old system is retired.

## Slide 10
12-month implementation roadmap
A controlled sequence with stage gates
1. Discover and scope
Month 1-2
Process map, data assessment, governance setup
2. Fit-to-standard design
Month 3-4
Define Day-1 scope and deltas
3. Build and test
Month 5-7
Configure, migrate, integrate, and test
4. Pilot site go-live
Month 8-9
Controlled cutover and hypercare
5. Rollout and stabilise
Month 10-12
Expand to remaining locations
Stage gates
Scope sign-off -> design sign-off -> data readiness -> cutover rehearsal -> go/no-go decision
Notes: Describe this as a gated roadmap rather than a fixed-date promise. The early months are for understanding processes, data and dependencies. The mid-stage is for design and build, but only after the scope has been frozen. The later months should be focused on a pilot, hypercare and then gradual rollout to the remaining sites.

## Slide 11
Governance and operating model
Who owns what during the programme
Executive Steering Committee
Board-level sponsorship, decisions, escalation
PMO
Plan, status, budget, RAID log
Business process owners
Finance, ops, procurement, engineering
Data governance
Master data, cleansing, sign-off
Technical team
Build, test, integrate, deploy
Control mechanisms
Weekly status reviews, formal change control, data quality checkpoints, test sign-offs, and cutover rehearsals. Business owners should approve process decisions; the steering committee should approve scope changes.
Notes: The governance slide shows that this is a management programme as much as an IT programme. Executives do not need to approve every task, but they do need to own the major trade-offs. Business process owners are important because they prevent the project from drifting into an IT-only mindset. The control mechanisms are there to keep the plan honest and to make decisions visible.

## Slide 12
Top risks and next steps
What leadership should watch most closely
Risk matrix
High
Impact
High
Probability
Data defects
Scope creep
Cutover risk
Adoption gap
Immediate next steps
1. Confirm the pilot site and executive sponsor
2. Appoint business process owners and data owners
3. Freeze Day-1 scope and agree the change process
4. Start data cleansing and interface mapping
5. Build the detailed project plan and test strategy
Notes: Finish by highlighting the four risks most likely to hurt the programme: data defects, scope creep, cutover disruption and adoption failure. Then shift to action: pilot site, sponsors, scope freeze, data work and the detailed plan. This gives the executives a clear sense that the programme is controllable and that the next decisions are concrete.